## Sheet1
Date | Day | StartTime | EndTime | Minutes | Description
2023-04-15 | Sat | 17:00 | 19:00 | 2 hours | Setup board and DHT11
2023-04-17 | Mon | 15:00 | 17:00 | 2 hours | Setup to output temps and humidity to terminal
2023-04-18 | Tues | 19:00 | 22:45 | 3:45 hours | Setup ESP8622, AT cmd working and able to connect to wifi
2023-04-21 | Fri | 15:00 | 17:00 | 2 hours | Setting up power supply module and refining previous code/debugging.
2023-04-24 | Mon | 15:00 | 17:00 | 2 hours | More debugging/cleaning up code/removing unnecessary code.
2023-04-26 | Weds | 15:00 | 17:00 | 2 hours | Implementation of fan/dc motor. Basic functionality completed.
2023-04-28 | Fri | 11:00 | 15:00 | 4 hours | Setting up integration of fan module with Blynk IoT application.
2023-04-29 | Sat | 15:00 | 21:00 | 6 hours | Fan/Blynk integration cont.
2023-04-30 | Sun | 11:00 | 16:00 | 5 hours | Fan/Blynk integration finished.
2023-05-01 | Mon | 15:00 | 17:00 | 2 hours | Setup notifications and cleaning up wiring.
2023-05-02 | Tues | 14:00 | 17:00 | 3 hours | Finish documentation.